## DFD MOD
Taran Laval - SAAA Builder 7417 Van's Aircraft RV7 - 73918
Deviation from Design & Modification Register |  |  |  | VH-TJL
Print Date: |  |  | 2016-04-06
| Type | Number | Title | Date | Status | FU | Part | Key
| DfD | DfD-0001 | HS411 Bearing Assembly - Change of Recommended Rivet | 2011-07-15 | I | N | Hstab | C | Compliant/Complete
| DfD | DfD-0002 | Horizontal Stabiliser Front Spar – Elongated Holes | 2012-04-12 | I | N | Hstab | N | Non-Compliant / Unactioned
| DfD | DfD-0003 | Minor Rivet Set Damage to HS-710 | 2012-04-14 | I | N | Hstab | R | Repeat Inspection Reqd
| DfD | DfD-0004 | RH HS404 Flange Damage | 2012-04-14 | I | N | Hstab | I | Info Only Item
| DfD | DfD-0005 | RH HS404-HS710-HS405 Hole Elongation | 2012-04-19 | I | N | Hstab | X | Cancelled
| DfD | DfD-0006 | RHS VS Skin Mid Mis-Dimple | 2012-06-15 | X | N | Vstab
| DfD | DfD-0007 | RHS VS Skin Upper Fwd Mis-Dimple | 2012-06-15 | X | N | Vstab
| DfD | DfD-0008 | VS-706 Mis Dimple | 2012-11-10 | I | N | Vstab
| DfD | DfD-0009 | VS oversize hole | 2012-11-25 | I | N | Vstab
| DfD | DfD-0010 | Restarting of Vertical Stabiliser | 2012-07-17 | I | N | Vstab
| DfD | DfD-0011 | Misdimpled Rudder Skin | 2013-01-20 | R | Y | Rudd
| DfD | DfD-0012 | RUDDER FWD COUNTERBALANCE ISSUE | 2013-05-04 | I | N | Rudd
| DfD | DfD-0013 | LH HORIZ STAB HOLD ELONGATION | 2013-05-31 | I | N | Hstab
| DfD | DfD-0014 | ELEVATOR RHS COUNTERSINK ELONGATION | 2014-02-28 | I | N | Relev
| DFD | DfD-0015 | ELEVATOR RHS AFT UPPER HOLE RIVET CHANGE | 2014-03-13 | I | N | Relev
| DfD | DfD-0016 | LH ELEVATOR HOLE CRACKING | 2014-04-03 | I | N | Lelev
| DFD | DFD-0017 | LH ELEVATOR RIVET CHANGE | 2014-04-03 | I | N | Lelev
| MOD | MOD-001 | LH ELEVATOR TRIM TAB/ELEVATOR RIB ADDITION | 2014-04-22 | I | N | LELEV
| DFD | DFD-0018 | LH ELEVATOR TRIM TAB OB RIB EDGE DISTANCE | 2014-05-05 | R | Y | Lelev
| DFD | DFD-0019 | LH WING SPAR TIEDOWN MARKS | 2014-09-30 | I | N | LWING
| MOD | MOD-002 | UPPER WING SINGLE PIECE SKIN | 2014-10-02 | X | N | WING
| DFD | DFD-0020 | LH WING MAIN RIB TO FWD SPAR DAMAGE | 2014-11-11 | I | N | LWING
| MOD | MOD-003 | CHANGED PITOT SYSTEM | 2014-11-12 | I | N | LWING
| DFD | DFD-0021 | REVISED TANK FITTING METHOD | 2014-12-08 | I | N | WING
| DFD | DFD-0022 | FUEL TANK IB SPAR ATTACH RIVET CHANGE | 2015-11-09 | I | N | WING
| MOD | MOD-004 | STALL WARN DELETE | 2015-12-14 | I | N | WING
| MOD | MOD-005 | LANDING LIGHT ADDITION | 2016-01-12 | I | N | WING
| DFD | DFD-0023 | RIGHT WING REAR SPAR CORROSION | 2016-02-15 | R | Y | RWING
| DfD | DFD-0024 | LH WING LEADING EDGE UNSATISFACTORY RIVET | 2015-11-17 | R | Y | LWING
| DfD | DFD-0025 | WING LEADING EDGE RIB-SPAR RIVET CHANGE | 2016-04-05 | I | N | WING

## SB AD
Taran Laval - SAAA Builder 7417 Van's Aircraft RV7 - 73918
Service Bulletin & Airworthiness Directive Compliance |  |  |  | VH-TJL
Print Date: |  |  | 2016-04-06
| Type | Number | Title | Date | Status | Key
| SB | SB 07-2-6 | Passenger Control Stick Safetying | 2007-02-06 | N | C | Compliant/Complete
| SB | SB 07-4-12 | Electric flap bearing retention | 2007-04-11 | N | N | Non-Compliant / Unactioned
| SB | SB 12-08-14 | AN4 bolt installation, wing attach. | 2012-08-14 | N | R | Repeat Inspection Reqd
| SB | SB 14-01-31 | Cracking near the bend in horizontal stabilizer front spar | 2014-01-31 | R | I | Info Only Item
| SB | SB 14-02-05 | Cracking in elevator spar web near elevator attach points | 2014-02-05 | R | X | Cancelled/Superseded
| SAIB | HQ-14-16 | Standard Hardware - Inspect All MS 21042 Nuts | 2014-04-28 | R

## Sign off sheet
Taran Laval - SAAA Builder 7417 Van's Aircraft RV7 - 73918
Annual Inspection DFD/SB/AD Compliance Checklist |  |  |  | VH-TJL
Print Date: |  |  | 2016-04-06
| Type | Number | Title | Date | Status