## Sheet1
work_log_id | post | POSTED BY | manual_ref_number | sub category | main category | date | hours | short_description
2 | Today I Ordered the full RV7 kit from Van's Aircraft, and the AirVenture FULL RV Tool Kit from Isham inc. | Taran |  | Miscellaneous | Miscellaneous | 2011-04-13 | 0 | Ordering
3 | Today The empennage kit arrived | Taran |  | Empennage | Empennage | 2011-04-28 | 0 | Arrival
4 | *Completed Empennage Harware Inventory *Started Part Inventory Completed Sub Kits 1, 2, 3 & 8 | Taran |  | Empennage | Empennage | 2011-05-01 | 1.5 | Inventory
5 | *Started Part Inventory Completed Sub Kits 4, 5, 6 & 7 Now finished inventorying the empennage kit | Taran |  | Empennage | Empennage | 2011-05-08 | 2 | Inventory 2
6 | Today i finished my second practise kit (the control surface piece) now i'm ready to start the empennage. | Taran |  | Miscellaneous | Miscellaneous | 2011-06-16 | 0 | Practise Kits Complete
7 | Today I Completed step one, which is: *Breaking The edges of both HS609PP bars *Checking bend of spar channel (HS603PP) in relation to HS609PP *Rounding the ends of HS-609PP Bars COMPLETED STEP 1 | Taran | HS/R.S ASSY/S1 | Horizontal Stabiliser | Empennage | 2011-06-17 | 0.42 | Rear Spar Assy. HS609pp Bar
8 | TODAY I SMOOTHED THE EDGES AND FACES OF THE HS609PP BARS. THERE WAS A BIT OF SCRATCHING IN ONE OF THEM, BUT I WAS ABLE TO SAND THEM OUT. NEXT I CLECOED THE STIFFENER BARS TO THE SPAR CHANNEL AND FINAL DRILLED ALL THE HOLES. I THEN ENLARGED THE HS708 ATTACHMENT HOLES TO #21 SIZE THEN I CLECOED HS412/413 BRACKETS TO SPAR CHANNEL AND MATCH DRILLED THEM WITH A #30 DRILL. NEXT I MATCH DRILLED THE HS411APP THROUGH THE HS411BPP BUT I WASN'T HAPPY WITH THE ALIGNMENT OF THE HOLES SO I SCRAPPED THEM AND HAVE ORDERED NEW ONES FROM VAN'S. COMPLETED STEPS 2, 3, 4, 5 | Taran | HS/R.S ASSY/S2-7 | Horizontal Stabiliser | Empennage | 2011-06-26 | 3.3 | HORIZONTAL STABILISER - REAR SPAR ASSY
9 | TODAY I -CLECOED HS-710 (REINFORCEMENT ANGLE) & HS714 (SPLICE ANGLE) TO HS702 (FWD SPAR CHANNELS) -MATCH DRILLED HOLES INBOARD OF HS404/5 RIB ATTACH POINTS -TAPERED THE ENDS OF HS714 AS PER DRAWING 3 | Taran | HS/F.S ASSY/S1-3 | Horizontal Stabiliser | Empennage | 2011-06-27 | 1.34 | HORIZONTAL STABILISER - FWD SPAR ASSY 2
10 | TODAY I -TAPERED THE ENDS OF HS710 AS PER DRAWING 2 -BENT THE ENDS OF 710 & 714 TO 6 DEGREE ANGLE AS PER DRAWING 3 -TRIMMED IB ENDS OF HS702 AS PER "FRONT SPAR TAB DETAIL" DRAWING 3 -MARKED BEND LINE ON HS702 #1 AND CUT AND TIDIED UP RELIEF NOTCH STEPS 3 & 4 COMPLETE | Taran | HS/F.S ASSY/S3-7 | Horizontal Stabiliser | Empennage | 2011-07-03 | 1.67 | HORIZONTAL STABILISER - FWD SPAR ASSY 3
11 | TODAY I -TRIMMED THE IB ENDS OF 2ND HS702 AS PER "FRONT SPAR TAB DETAIL" DRAWING 3 -MARKED BEND LINE AND CUT RELIEF NOTCH ON HS702 #2 -I FOUND SOME DEEP SCRATCHING AT THE RELIEF NOTCH ON HS702 #1 SO I HAVE BLENDED THEM OUT AND EMAILED VANS WITH MEASUREMENTS AND PHOTOS -WHILE I WAIT FOR THE RESULTS FROM VANS I'LL BUILD ON AND REDO HS702 #1 IF NEED BE. -BENT TABS ON HS 702 #1&2 AS PER VIEW B-B DRAWING 3 -COUNTERSUNK CENTER FOUR HOLES ON HS710 & 714 & DIMPLED CENTER FOUR HOLES ON HS702. STEPS 5, 6, 7, 8, 9 COMPLETE | Taran | HS/F.S ASSY/S5-9 | Horizontal Stabiliser | Empennage | 2011-07-04 | 2.17 | HORIZONTAL STABILISER - FWD SPAR ASSY 4